## ToDo
Task List
✓ | Tasks | PIC | Draft | Expected Finish Date | Comment
Basic Game
Stage Layout (the platform game)
FALSE | - Background | Any | 2023-05-24 |  | - need update of level size and image and final lauout
FALSE | - Obstacle | Greshka
FALSE | - Timer(Done) and Lives Bar | Fynn
Animations
FALSE | - Movement of the Character(included input) | Greshka
TRUE | - Camera | Any |  | 2023-05-24
Collision
FALSE | - Character and level object | Any, Greshka | 2023-05-25 |  | - Hitboxes (L, R, Buttom) done, left and right hand side ready. - Buttom part need to be check
TRUE | - game edge | Any |  | 2023-05-25 | ...... bugs found, camera still updating after reaching the right handside edge...... not the first privorty... fix it if we hv time... (Any)
FALSE
Pop up Screen<?>
TRUE | -Start/Pause Menu/Main Menu | Nathan |  | 2023-05-30 | Pause menu opens but does not pause the game yet. Main Menu has been implemented.
FALSE | -GameOver Screen | Nathan
The First Mini Game (a puzzle game?)
FALSE | -First Mini Game | Nathan
TRUE | -Second Mini Game | Fynn
Game Audio
FALSE | -Background Music Creation And Implementation | Nathan
FALSE | -Common Sound Effects Implementation | Nathan |  |  | Audio Class Created Just need samples